## Sheet1
Tue, 12 Apr 2016 14:32:26 +0100	Changed the layout/structure of the application.
Sat, 9 Apr 2016 21:06:13 +0100	Stream button now only appears when the file type of the file uploaded can be streamed.
Tue, 5 Apr 2016 18:49:34 +0100	Refactored styling of the site.
Tue, 5 Apr 2016 15:28:27 +0100	Changed port the application runs on and put the application live on an AWS ec2 instance.
Tue, 5 Apr 2016 00:23:09 +0100	Added authentication to rooms via a password page.
Sat, 2 Apr 2016 23:51:00 +0100	Design pretty much finished, rooms now disconnect and display amount of users to uploader. I added fucntionality to improve performance by removing unused rooms/peer connections when they are done with.
Thu, 24 Mar 2016 16:08:38 +0000	One to many peer connections now working! I have started to work on design of site.
Wed, 23 Mar 2016 14:56:35 +0000	Node implementation is now working for downloading and streaming files.
Wed, 16 Mar 2016 00:13:19 +0000	Still working on refactoring the signalling server to a node server implementation.
Tue, 15 Mar 2016 00:31:21 +0000	I decided to abandon the Spring signalling server as it doesn't have the functionality needed for multiple peer connections. I have started to work on a node server implementation.
Tue, 23 Feb 2016 20:11:10 +0000	attempting to make the signalling server deal with multiple one-to-one connections
Sun, 31 Jan 2016 21:06:41 +0000	partially finished multiple peer connections; need to work on signalling with multiple peer connections in action.
Sun, 31 Jan 2016 17:14:13 +0000	Audio streaming fixed; attempting to get multiple peer connections working again.
Tue, 26 Jan 2016 18:23:22 +0000	Audio streaming broke when I was attempting one to many peer connections, attempting to fix it at the moment.
Fri, 22 Jan 2016 19:08:14 +0000	Started to work on one to many peer connections.
Thu, 21 Jan 2016 16:31:41 +0000	Refactored project to work in firefox; chrome is no longer supported as it relies on file chunking to transfer files.
Thu, 24 Dec 2015 16:32:51 +0000	added basic file transfer functionality; added basic audio streaming functionality. Video streaming cannot be supported as video files cannot be converted to a stream by any
Tue, 22 Dec 2015 01:11:19 +0000	Added basic datachannel functionality; refactored so that app.js only communicates with p2p.js which then communicates with signaller.js
Mon, 21 Dec 2015 00:48:39 +0000	Added basic webrtc peerconnection functionality; restructured javascript dependencies to use bower ;moved client side signalling functionality into it's own javascript file;
Tue, 15 Dec 2015 15:01:49 +0000	Finished room generation for signalling server.
Wed, 9 Dec 2015 23:49:33 +0000	Attempting to add dynamic url routing to signalling server for room pages
Thu, 3 Dec 2015 00:20:32 +0000	Started to prototype dynamic url/room generation for the signalling server.
Tue, 1 Dec 2015 21:12:11 +0000	Decided not to go with a framework for the client side as it seems unnecessary. Got a partially working web app prototype to test signalling server with.
Mon, 30 Nov 2015 19:05:46 +0000	Experimenting with backbone.js client-side web application framework
Wed, 25 Nov 2015 21:48:02 +0000	Finished the first prototype of the Spring signalling server.
Mon, 16 Nov 2015 17:15:54 +0000	Added ethics form to the interim report.
Fri, 13 Nov 2015 14:47:38 +0000	Finished first draft of the interim report.
Thu, 12 Nov 2015 18:49:53 +0000	updated interim report
Tue, 3 Nov 2015 20:48:56 +0000	updated interim report
Mon, 2 Nov 2015 19:35:24 +0000	Still working on the interim report.
Tue, 27 Oct 2015 16:21:17 +0000	Started the interim report in LaTeX.
Wed, 21 Oct 2015 15:55:31 +0100	Finalised the project proposal.
Tue, 20 Oct 2015 18:55:31 +0100	updated project proposal
Mon, 19 Oct 2015 13:00:59 +0100	Updated the project proposal with a Gantt chart
Fri, 16 Oct 2015 13:06:14 +0100	I have drafted the project proposal and started to experiment with the Spring web framework and the STOMP websocket library.